Project Name: arthur-project

# Plan of actions

16-12-2024

|  |  |  |
| --- | --- | --- |
| **Task** | **Estimate**  **(day)** | **status** |
| Installing Laravel 11, preparing repository, database design | 2 (16-12-24 to 17-12-24) | done |
| Add frontend & add admin panel | 2 (18-12-24 to 19-12-24) | done |
| Frontend Crud & Admin login+crud | 3 (20-12-24 to 22-12-24) |  |
| User registration, login, password reset etc | 1 (23-12-24) |  |
| Appointment section | 2 (24-12-24 to 25-12-24) |  |
| **Total estimated hours so far:** | **10** |  |
| **END OF PHASE 1** | | |
| Payments system with paypal And the list of orders on admin panel | **4** (26-12-24 to 29-12-24) | **Question:** do you need email invoices sent for the payments? Or, alternatively, you can get the invoices directly from paypal, after the payment, and send them manually. |
| SEO | **1** (30-12-24) | Make sitemap and Add it in google, yahoo |